## How to use
SME IPO readiness tracker
vikashkhanal.in · free template · last reviewed 6 Oct 2026 · not professional advice
What this workbook does
A working plan for a company preparing an SME IPO on BSE SME or NSE Emerge. The Tracker sheet lists the readiness tasks in seven workstreams; the Eligibility sheet tests three years of restated numbers against the exchange financial criteria; the Dashboard counts progress.
How to use it
• | Tracker: enter the target DRHP filing date in cell C3. Due dates default to that date minus the 'weeks before DRHP' in column G. Overwrite any due date by typing a date in column H (the formula column I picks it up).
• | Set Status from the dropdown. RAG turns red when a task is Blocked or overdue, amber when due within 14 days (change the window in C4), green otherwise.
• | 'Depends on #' takes the row number of another task; column O then shows that task's status so you can see what is holding you up.
• | Eligibility: fill the yellow cells with restated figures (₹ lakh). Thresholds sit in the parameter block so you can update them if an exchange revises its criteria.
• | Add rows at the bottom of the Tracker by copying the last row down. Keep the formulas in the grey columns.
Colour key
Yellow fill, blue text: input cells you edit.
Grey fill: formulas. Do not overwrite.
Rule basis (as on 6 Oct 2026)
• | SEBI ICDR Chapter IX (SME issues), as amended in March 2025: operating profit (EBITDA) of ₹1 crore from operations in any 2 of the 3 preceding years (Reg 229); offer for sale capped at 20% of issue size and 50% of each seller's holding; general corporate purposes capped at 15% or ₹10 crore; no repayment of promoter / related-party loans from proceeds; DRHP open for public comments for 21 days.
• | NSE Emerge: positive net worth; positive free cash flow to equity (FCFE) in at least 2 of 3 years. FCFE per NSE circular of 20 Apr 2026 = cash flow from operations − purchase of fixed assets + proceeds from issue of capital + net borrowings − interest × (1 − tax rate).
• | BSE SME (as published by the exchange; verify the current version before relying on it): net tangible assets of at least ₹3 crore in the last full year; net worth of at least ₹1 crore in each of the last 2 full years; leverage (debt / equity) not above 3:1; post-issue paid-up capital not above ₹25 crore.
Exchange criteria change often. Re-check the exchange's eligibility page and the latest circulars, and confirm every test with your lead manager. Definitions of net worth, NTA and borrowings follow the exchange's own definitions, which can differ from these simplified formulas.
Disclaimer
A working aid, not legal, investment or professional advice. Prepared by Vikash Khanal (vikashkhanal.in). Confirm against SEBI ICDR, LODR, the Companies Act 2013 and the exchange's current criteria with your company secretary, auditor and lead manager.

## Dashboard
Progress by workstream
Counts update from the Tracker sheet
Workstream | Not started | In progress | Blocked | Done | N/A | Red | Amber | % done (excl. N/A)
Corporate
Board & KMP
Capital & demat
Financials & restatement
Tax, GST, TDS, FEMA, MSME
Legal & assets
Issue structure
Total

## Tracker
IPO readiness tracker
Target DRHP filing date |  | 2027-03-31 | ← example date; type your own
Amber window (days) |  | 14
As-on date |  |  | ← TODAY() by default; type a fixed date to freeze the view
# | Workstream | Task | Rule / reference | Owner | Start date | Weeks before DRHP | Due date (override) | Due date | Status | Days to due | RAG | Depends on # | Dependency note | Dependency status | Notes / evidence
1 | Corporate | Convert private company to public limited: board approval, special resolution, alter MoA/AoA, file MGT-14 and INC-27 | Companies Act 2013 s.14, s.18; Rule 41 Incorporation Rules | CS |  | 26 |  |  | Not started |  |  |  | Do first: SME IPO needs a public company
2 | Corporate | Increase authorised capital to cover bonus / pre-IPO allotment / fresh issue; alter capital clause; file SH-7 | s.61, s.13, s.64 | CS |  | 24 |  |  | Not started |  |  | 1 | Size it after the cap table is fixed (#21)
3 | Corporate | Update statutory registers (MGT-1 members, directors and KMP, charges) and minute books since incorporation | s.88, s.170, s.85, s.118 | CS |  | 22 |  |  | Not started
4 | Corporate | Bring MCA filings current: AOC-4, MGT-7/7A, DIR-3 KYC, DPT-3, MSME-1, ADT-1; regularise delays | MCA21 V3 master data | CS |  | 22 |  |  | Not started |  |  |  | Lead manager will ask for a filing-status certificate
5 | Corporate | Reconcile charge register with MCA index; file CHG-4 for loans already repaid | s.77, s.82 | CS / CFO |  | 20 |  |  | Not started
6 | Corporate | Review every past allotment and transfer: PAS-3, valuation reports, s.42 / s.62 compliance, FC-GPR where foreign investors | s.42, s.62; FEMA (Non-debt Instruments) Rules 2019 | CS / Legal |  | 20 |  |  | Not started |  |  |  | Gaps here need compounding or rectification before DRHP
7 | Corporate | Identify promoters, promoter group and group companies; collect KYC and declarations | SEBI ICDR Reg 2(1)(oo), 2(1)(pp); group company materiality policy | CS / LM |  | 18 |  |  | Not started
8 | Corporate | Functional company website with investor section | Exchange eligibility (BSE SME) | Marketing / CS |  | 12 |  |  | Not started
9 | Board & KMP | Appoint independent directors (at least one-third of the board), confirm registration in the ID databank | s.149(4), s.149(6), s.150; Rule 6 Appointment and Qualification of Directors Rules | Board / CS |  | 20 |  |  | Not started |  |  | 1 | Needs public-company status (#1)
10 | Board & KMP | Appoint at least one woman director | s.149(1) second proviso; Rule 3 | Board / CS |  | 20 |  |  | Not started |  |  | 1
11 | Board & KMP | Appoint KMP: MD / WTD / CEO, CFO, company secretary; file DIR-12 and MR-1 where needed | s.196, s.203; Schedule V | Board / CS |  | 20 |  |  | Not started |  |  | 1
12 | Board & KMP | Designate company secretary as compliance officer | SEBI LODR Reg 6 | Board |  | 16 |  |  | Not started |  |  | 11
13 | Board & KMP | Constitute audit committee, NRC and (if more than 1,000 security holders) stakeholders' relationship committee; adopt terms of reference | s.177, s.178(1), s.178(5) | Board / CS |  | 18 |  |  | Not started |  |  | 9 | Needs independent directors (#9)
14 | Board & KMP | Adopt policies: vigil mechanism, NRC policy, RPT policy, Reg 30 materiality, preservation of documents, PIT codes | s.177(9), s.178(3); LODR Reg 9, 23, 30; PIT Reg 8, 9 | CS |  | 14 |  |  | Not started |  |  | 13
15 | Board & KMP | Collect director and KMP declarations: DIR-8, MBP-1, DIR-2, wilful defaulter / fugitive offender checks | s.164, s.184; ICDR Reg 228 | CS / LM |  | 14 |  |  | Not started |  |  |  | Any 'yes' here can make the company ineligible
16 | Capital & demat | Obtain ISIN; sign tripartite agreements with NSDL, CDSL and the RTA | Depositories Act 1996; Rule 9A Prospectus and Allotment Rules | CS / RTA |  | 22 |  |  | Not started |  |  | 1
17 | Capital & demat | Dematerialise all promoter and promoter-group shares (100%) and as many other holdings as possible | ICDR SME requirement; Rule 9A | CS / RTA |  | 16 |  |  | Not started |  |  | 16
18 | Capital & demat | Compute minimum promoter contribution (20% of post-issue capital) and eligible securities; plan lock-in | ICDR Reg 236, 237, 238 (SME chapter IX) | CFO / LM |  | 14 |  |  | Not started |  |  | 21 | 3-year lock-in on minimum contribution; staged release of excess
19 | Capital & demat | Pre-IPO bonus / rights / private placement: pricing, valuation, s.62 approvals | s.62, s.63; ICDR eligible-securities tests | CFO / CS |  | 18 |  |  | Not started |  |  | 2
20 | Capital & demat | Terminate or make fall away on listing any special rights in shareholder agreements | Articles; ICDR | Legal |  | 12 |  |  | Not started
21 | Capital & demat | Finalise pre-issue and post-issue cap table; confirm post-issue paid-up face value within ₹25 crore | ICDR Reg 229 | CFO / LM |  | 16 |  |  | Not started |  |  |  | See Eligibility sheet
22 | Financials & restatement | Statutory audits complete for 3 full years (and stub period, if any) by a peer-reviewed auditor | ICDR Schedule VI; ICAI peer review | CFO / Auditor |  | 16 |  |  | Not started
23 | Financials & restatement | Restated financial statements with restatement adjustments, notes and examination report | ICDR Schedule VI; ICAI Guidance Note on Reports in Company Prospectuses | Auditor / CFO |  | 10 |  |  | Not started |  |  | 22
24 | Financials & restatement | Clear or explain audit qualifications, CARO 2020 remarks and emphasis of matter | CARO 2020 | CFO |  | 12 |  |  | Not started |  |  | 22
25 | Financials & restatement | KPI pack with auditor certificate; draft MD&A for the restated period | ICDR Schedule VI (KPI disclosures) | CFO / LM |  | 8 |  |  | Not started |  |  | 23
26 | Financials & restatement | Statement of special tax benefits, capitalisation statement, statement of financial indebtedness | ICDR Schedule VI | Auditor / CFO |  | 8 |  |  | Not started |  |  | 23
27 | Financials & restatement | Related-party list and RPT reconciliation for the restated period | AS 18 / Ind AS 24; s.188 | CFO / CS |  | 10 |  |  | Not started
28 | Financials & restatement | Working-capital assessment and cost estimates supporting the objects of the issue | ICDR Schedule VI (objects) | CFO / LM |  | 8 |  |  | Not started |  |  |  | Quotations / CA certificate for capex objects
29 | Tax, GST, TDS, FEMA, MSME | Income-tax: return status, open assessments, outstanding demands on the portal; responses filed | Income-tax Act 2025 / 1961 | CFO / Tax |  | 14 |  |  | Not started |  |  |  | Litigation disclosure feeds DRHP
30 | Tax, GST, TDS, FEMA, MSME | TDS: clear TRACES defaults (short deduction, late payment, late filing); issue certificates | s.392, s.393 [192-195]; TRACES | Finance |  | 12 |  |  | Not started
31 | Tax, GST, TDS, FEMA, MSME | GST: GSTR-1 / 3B / 9 / 9C status for every GSTIN, ITC vs GSTR-2B reconciliation, open notices | CGST Act 2017 s.37, 39, 44, 61, 73/74 | Finance |  | 12 |  |  | Not started
32 | Tax, GST, TDS, FEMA, MSME | FEMA: close open IDPMS / EDPMS entries, file pending FC-GPR / ODI / FLA returns | FEMA 1999; RBI Master Directions on import and export | Finance / AD bank |  | 12 |  |  | Not started |  |  |  | Open entries show up in bank diligence
33 | Tax, GST, TDS, FEMA, MSME | MSME: clear dues beyond 45 days, file MSME-1, quantify s.37(2)(g) [43B(h)] add-back | MSMED Act 2006 s.15, s.16, s.22 | Finance |  | 10 |  |  | Not started |  |  |  | Use the MSME 45-day template
34 | Tax, GST, TDS, FEMA, MSME | PF / ESI / professional tax / labour code returns and dues | EPF Act, ESI Act, state PT laws | HR / Finance |  | 10 |  |  | Not started
35 | Tax, GST, TDS, FEMA, MSME | List undisputed statutory dues outstanding over six months | CARO 2020 para 3(vii) | Finance |  | 8 |  |  | Not started
36 | Legal & assets | Title documents for owned property; leases registered and stamped | Registration Act 1908; state Stamp Acts | Legal |  | 14 |  |  | Not started
37 | Legal & assets | Register of licences and approvals: factory, pollution, IEC, GST, Shops & Establishments, trade licences | Various | Legal / Admin |  | 12 |  |  | Not started
38 | Legal & assets | Trademarks and other IP registered in the company's name | Trade Marks Act 1999 | Legal |  | 12 |  |  | Not started
39 | Legal & assets | Lender consents / NOCs for the IPO, change in shareholding and board | Loan agreements | CFO |  | 10 |  |  | Not started |  |  |  | Banks can take 4 to 8 weeks
40 | Legal & assets | Litigation register for company, promoters, directors, group companies against the materiality policy | ICDR Schedule VI | Legal / CS |  | 10 |  |  | Not started |  |  | 7
41 | Legal & assets | Insurance coverage review; fixed-asset register reconciled and physically verified | CARO 2020 para 3(i) | CFO |  | 10 |  |  | Not started
42 | Issue structure | Appoint SEBI-registered lead manager; sign engagement letter | ICDR Reg 245; SEBI (Merchant Bankers) Regulations | Board / CFO |  | 26 |  |  | Not started |  |  |  | LM drives the timetable
43 | Issue structure | Appoint RTA, legal counsel, peer-review auditor for restatement, market maker, underwriter | ICDR Reg 260, 261 (underwriting, market making) | Board / LM |  | 20 |  |  | Not started |  |  | 42 | Market making is mandatory for SME issues
44 | Issue structure | Objects of the issue: general corporate purposes within 15% of the amount raised or ₹10 crore, whichever is lower; no repayment of promoter / related-party loans | ICDR Reg 230 (as amended 2025) | CFO / LM |  | 10 |  |  | Not started |  |  | 28
45 | Issue structure | Offer for sale within 20% of issue size; each selling shareholder within 50% of pre-issue holding | ICDR Reg 230 (as amended 2025) | LM |  | 10 |  |  | Not started |  |  | 21
46 | Issue structure | Choose platform (BSE SME or NSE Emerge); run the Eligibility sheet; pre-filing meeting with the exchange | Exchange eligibility criteria | CFO / LM |  | 12 |  |  | Not started |  |  | 23
47 | Issue structure | Board approval of the IPO; shareholders' special resolution under s.62(1)(c); constitute IPO committee | s.23, s.62(1)(c) | Board / CS |  | 8 |  |  | Not started |  |  | 1
48 | Issue structure | Draft DRHP; due diligence; file with exchange; 21-day public comment period | ICDR Reg 246, 247 | LM |  | 0 |  |  | Not started |  |  | 23
49 | Issue structure | Monitoring agency where the issue size crosses the threshold | ICDR Reg 262 (threshold: verify) | LM |  | 0 |  |  | Not started |  |  |  | Confirm the current threshold with the LM
50 | Issue structure | Agreements: issue agreement, RTA, market making, underwriting, escrow / sponsor bank (UPI) | ICDR | LM / Legal |  | 4 |  |  | Not started |  |  | 43
51 | Issue structure | Post-listing compliance calendar: half-yearly results within 45 days, Reg 30 disclosures, PIT structured digital database | LODR Reg 33, Reg 30; PIT Reg 3(5) | CS |  | 0 |  |  | Not started |  |  | 14

## Eligibility
SME IPO financial eligibility test
All amounts in ₹ lakh (1 crore = 100 lakh). Use restated figures. Year 3 is the latest completed financial year.
Restated figures (₹ lakh) | Year 1 (oldest) | Year 2 | Year 3 (latest) | Notes
Financial year label | FY 2023-24 | FY 2024-25 | FY 2025-26
Profit and loss
Profit before tax | 180 | 260 | 420 | From restated P&L
Add: finance costs | 95 | 110 | 120
Add: depreciation and amortisation | 40 | 55 | 70
Less: other income | 12 | 18 | 25 | Operating profit is from operations, so other income is excluded
Operating profit (EBITDA from operations) |  |  |  | PBT + finance costs + D&A − other income
Balance sheet (year end)
Paid-up equity share capital | 100 | 100 | 500
Reserves and surplus / other equity | 520 | 700 | 520
Less: revaluation reserve | 0 | 0 | 0 | Exclude for net worth
Less: miscellaneous expenditure not written off / accumulated losses not netted | 0 | 0 | 0
Net worth |  |  |  | Capital + reserves − revaluation reserve − misc. expenditure
Intangible assets (incl. goodwill, intangibles under development) | 5 | 6 | 8
Deferred tax assets (net) | 3 | 4 | 4
Net tangible assets |  |  |  | Net worth − intangibles − DTA (simplified; check the exchange definition)
Long-term borrowings (incl. current maturities) | 600 | 650 | 700
Short-term borrowings | 400 | 450 | 500
Total borrowings
Debt / equity (times) |  |  |  | Total borrowings ÷ net worth
Cash flow (for NSE FCFE)
Net cash from operating activities (after tax paid) | 150 | -20 | 310 | Restated cash flow statement
Purchase of PPE, CWIP and intangibles, net of sale proceeds | 220 | 90 | 160 | Enter as a positive number
Proceeds from issue of share capital (incl. premium) | 0 | 0 | 300 | Cash received only
Borrowings raised | 300 | 250 | 280
Borrowings repaid | 120 | 150 | 180 | Enter as a positive number
Net borrowings |  |  |  | Raised − repaid
Interest paid / finance cost | 95 | 110 | 120
Effective tax rate (t) | 25.17% | 25.17% | 25.17% | 25.17% for a company under the concessional regime (verify yours)
Free cash flow to equity (FCFE) |  |  |  | CFO − capex + equity raised + net borrowings − interest × (1 − t)
Parameters (edit if criteria change)
Minimum operating profit per year (₹ lakh) | 100 |  |  | SEBI ICDR Reg 229 (2025) / NSE: ₹1 crore in 2 of 3 years
Years out of 3 that must meet it | 2
BSE: minimum NTA in latest year (₹ lakh) | 300 |  |  | BSE SME published criteria (verify)
BSE: minimum net worth in each of last 2 years (₹ lakh) | 100 |  |  | BSE SME published criteria (verify)
BSE: maximum debt / equity (times) | 3 |  |  | BSE SME published criteria (verify)
NSE: FCFE positive in at least (years of 3) | 2 |  |  | NSE Emerge criteria; formula per NSE circular 20 Apr 2026
Maximum post-issue paid-up capital, face value (₹ lakh) | 2500 |  |  | ₹25 crore
Proposed post-issue paid-up capital, face value (₹ lakh) | 680 |  |  | Your cap table
Test | Result | Pass / fail | Platform | Basis
Years with operating profit ≥ threshold |  |  | Both (SEBI) | ICDR Reg 229; any 2 of 3 years
Net worth positive in latest year |  |  | NSE Emerge | Positive net worth
Years with positive FCFE |  |  | NSE Emerge | At least 2 of 3 years
Net tangible assets, latest year (₹ lakh) |  |  | BSE SME | ≥ ₹3 crore (verify)
Lower of net worth in last 2 years (₹ lakh) |  |  | BSE SME | ≥ ₹1 crore each year (verify)
Debt / equity, latest year |  |  | BSE SME | ≤ 3:1 (verify)
Post-issue paid-up capital (₹ lakh) |  |  | Both | ≤ ₹25 crore face value
NSE Emerge: all applicable tests
BSE SME: all applicable tests
Simplified tests for planning only. Exchanges also apply track-record, promoter, litigation, regulatory-action and other conditions. Example figures are illustrative; replace them.

## Lists
Workstreams | Status | RAG
Corporate | Not started | Red
Board & KMP | In progress | Amber
Capital & demat | Blocked | Green
Financials & restatement | Done | Done
Tax, GST, TDS, FEMA, MSME | N/A | N/A
Legal & assets
Issue structure